## Sheet1
Division | Division Description | CSI Code | CSI Description | Item Number | Item Description | Item Type | Submit Date Required | Actual Submit Date | Sub Submit Prep Time | Org Submit Prep Time | Submit Review Time | Lead Time | Total Lead Time | Required On Job Date | Procure By | Anticipated Delivery Date | Delivery Float | Notes | Transportation | Technical Data | Manufacturing Data
Division 03 | Concrete | 03 30 00 | Cast-In-Place Concrete | 001 | Mix Design A | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 03 | Concrete | 03 30 00 | Cast-In-Place Concrete | 002 | Mix Design B | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 03 | Concrete | 03 60 00 | Grouting | 001 | Grout Mixture | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 04 | Masonry | 04 20 00 | Unit Masonry | 001 | Mix Design A | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 04 | Masonry | 04 20 00 | Unit Masonry | 002 | Mix Design B | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 04 | Masonry | 04 20 00 | Unit Masonry | 003 | Alternate Mix Design | Alternate |  |  | 5 | 5 | 15 | 15 | 40 | 2023-04-27
Division 05 | Metals | 05 50 00 | Metal Fabrications | 001 | Aluminum Stair #1 - Product Data | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-06-27
Division 05 | Metals | 05 50 00 | Metal Fabrications | 002 | Aluminum Stair #1 - Shop Drawings | Shop Drawing |  |  | 5 | 5 | 15 | 15 | 40 | 2023-06-27
Division 07 | Thermal and Moisture Protection | 07 10 00 | Damp proofing and Waterproofing | 001 | EIFS Product Data | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 08 | Openings | 08 10 00 | Doors and Frames | 001 | Metal Door & Hardware Package | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 08 | Openings | 08 10 00 | Doors and Frames | 002 | Wood Door & Hardware Package | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 08 | Openings | 08 50 00 | Windows | 001 | Glazing Specifications | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 09 | Finishes | 09 30 00 | Tiling | 001 | Tile Sample Selections | Sample |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 10 | Specialties | 10 00 00 | Specialties | 001 | Toilet Partition Product Data | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 10 | Specialties | 10 14 00 | Signage | 002 | Bathroom Signage | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 21 | Fire Suppression | 21 00 00 | Fire Suppression | 001 | Shop Drawings & Layout | Shop Drawing |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 21 | Fire Suppression | 21 00 00 | Fire Suppression | 002 | Fire Suppression Calcs | Calculations |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 22 | Plumbing | 22 00 00 | Plumbing | 001 | Fixtures | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 23 | Heating, Ventilating, and Air Conditioning | 23 00 00 | HVAC | 001 | Air Handlers | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 23 | Heating, Ventilating, and Air Conditioning | 23 00 00 | HVAC | 002 | Louvers | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 26 | Electrical | 26 00 00 | Electrical | 001 | Electrical Calcs | Calculations |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 26 | Electrical | 26 00 00 | Electrical | 002 | Electrical Fixtures | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 31 | Earthwork | 31 00 00 | Landscaping | 001 | Fountain Decorations | Product Data |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Division 32 | Exterior Improvements | 32 17 23 | Pavement Markings | 001 | Special ADA Painting Layout | Shop Drawing |  |  | 5 | 5 | 15 | 15 | 40 | 2023-07-30
Note on N1: Samantha Leidy: Total Lead Time is calculated, not imported. This column simply shows the calculation

## Sample Standard Index
Division | Division Description | CSI Code | CSI Code Description
Division 01 | General Requirements | 01000 | General Requirements
Division 01 | General Requirements | 01100 | Summary
Division 01 | General Requirements | 01200 | Price and Payment Procedures
Division 01 | General Requirements | 01300 | Administrative Requirements
Division 01 | General Requirements | 01400 | Quality Requirements
Division 01 | General Requirements | 01500 | Temporary Facilities and Controls
Division 01 | General Requirements | 01600 | Product Requirements
Division 01 | General Requirements | 01700 | Execution Requirements
Division 01 | General Requirements | 01800 | Facility Operation
Division 01 | General Requirements | 01900 | Facility Decommissioning
Division 02 | Site Construction | 02000 | Site Construction
Division 02 | Site Construction | 02050 | Basic Site Materials and Methods
Division 02 | Site Construction | 02100 | Site Remediation
Division 02 | Site Construction | 02200 | Site Preparation
Division 02 | Site Construction | 02300 | Earthwork
Division 02 | Site Construction | 02400 | Tunneling, Boring, and Jacking
Division 02 | Site Construction | 02450 | Foundation and Load-bearing Elements
Division 02 | Site Construction | 02500 | Utility Services
Division 02 | Site Construction | 02600 | Drainage and Containment
Division 02 | Site Construction | 02700 | Bases, Ballasts, Pavements, and Appurtenances
Division 02 | Site Construction | 02800 | Site Improvements and Amenities
Division 02 | Site Construction | 02900 | Planting
Division 02 | Site Construction | 02950 | Site Restoration and Rehabilitation
Division 03 | Concrete | 03000 | Concrete
Division 03 | Concrete | 03050 | Basic Concrete Materials and Methods
Division 03 | Concrete | 03100 | Concrete Forms and Accessories
Division 03 | Concrete | 03200 | Concrete Reinforcement
Division 03 | Concrete | 03300 | Cast-in-Place Concrete
Division 03 | Concrete | 03400 | Precast Concrete
Division 03 | Concrete | 03500 | Cementitious Decks and Underlayment
Division 03 | Concrete | 03600 | Grouts
Division 03 | Concrete | 03700 | Mass Concrete
Division 03 | Concrete | 03900 | Concrete Restoration and Cleaning
Division 04 | Masonry | 04000 | Masonry
Division 04 | Masonry | 04050 | Basic Masonry Materials and Methods
Division 04 | Masonry | 04200 | Masonry Unity
Division 04 | Masonry | 04400 | Stone
Division 04 | Masonry | 04500 | Refractories
Division 04 | Masonry | 04600 | Corrosion-Resistant Masonry
Division 04 | Masonry | 04700 | Simulated Masonry
Division 04 | Masonry | 04800 | Masonry Assemblies
Division 04 | Masonry | 04900 | Masonry Restoration and Cleaning
Division 05 | Metals | 05000 | Metals
Division 05 | Metals | 05050 | Basic Metal Materials and Methods
Division 05 | Metals | 05100 | Structural Framing
Division 05 | Metals | 05200 | Metal Joist
Division 05 | Metals | 05300 | Metal Deck
Division 05 | Metals | 05400 | Cold-Form Metal Framing
Division 05 | Metals | 05500 | Metal Fabrications
Division 05 | Metals | 05600 | Hydraulic Fabrications
Division 05 | Metals | 05650 | Railroad Truck Accessories
Division 05 | Metals | 05700 | Ornamental Metal
Division 05 | Metals | 05800 | Expansion Control
Division 05 | Metals | 05900 | Metal Restoration and Cleaning
Division 06 | Wood and Plastics | 06000 | Woods & Plastics
Division 06 | Wood and Plastics | 06050 | Basic Materials and Methods
Division 06 | Wood and Plastics | 06100 | Rough Carpentry
Division 06 | Wood and Plastics | 06200 | Finish Carpentry
Division 06 | Wood and Plastics | 06400 | Architectural Woodwork
Division 06 | Wood and Plastics | 06500 | Structural Plastics
Division 06 | Wood and Plastics | 06600 | Plastic Fabrications
Division 06 | Wood and Plastics | 06900 | Wood and Plastic Restoration and Cleaning
Division 07 | Thermal & Moisture Protection | 07000 | Thermal and Moisture Protections
Division 07 | Thermal & Moisture Protection | 07050 | Basic Materials and Methods
Division 07 | Thermal & Moisture Protection | 07100 | Damp proofing and Waterproofing
Division 07 | Thermal & Moisture Protection | 07200 | Thermal Protection
Division 07 | Thermal & Moisture Protection | 07300 | Shingles, Roof Tiles, and Roof Coverings
Division 07 | Thermal & Moisture Protection | 07400 | Roofing and Siding Panels
Division 07 | Thermal & Moisture Protection | 07500 | Membrane Roofing
Division 07 | Thermal & Moisture Protection | 07600 | Flashing and Sheet Metal
Division 07 | Thermal & Moisture Protection | 07700 | Roof Specialties and Accessories
Division 07 | Thermal & Moisture Protection | 07800 | Fire and Smoke Protection
Division 07 | Thermal & Moisture Protection | 07900 | Joint Sealers
Division 08 | Doors and Windows | 08000 | Openings
Division 08 | Doors and Windows | 08050 | Basic Materials and Methods
Division 08 | Doors and Windows | 08100 | Metal Doors and Frames
Division 08 | Doors and Windows | 08200 | Wood and Plastic Doors
Division 08 | Doors and Windows | 08300 | Specialty Doors
Division 08 | Doors and Windows | 08400 | Entrances and Storefronts
Division 08 | Doors and Windows | 08500 | Windows
Division 08 | Doors and Windows | 08600 | Skylights
Division 08 | Doors and Windows | 08700 | Hardware
Division 08 | Doors and Windows | 08800 | Glazing
Division 08 | Doors and Windows | 08900 | Glazed Curtain Wall
Division 09 | Finishes | 09000 | Finishes
Division 09 | Finishes | 09050 | Basic Materials and Methods
Division 09 | Finishes | 09100 | Metal Support Assemblies
Division 09 | Finishes | 09200 | Plaster and Gypsum Board
Division 09 | Finishes | 09300 | Tile
Division 09 | Finishes | 09400 | Terrazzo
Division 09 | Finishes | 09500 | Ceilings
Division 09 | Finishes | 09600 | Flooring
Division 09 | Finishes | 09700 | Wall Finishes
Division 09 | Finishes | 09800 | Acoustical Treatment
Division 09 | Finishes | 09900 | Paints and Coatings
Division 10 | Specialties | 10000 | Specialties
Division 10 | Specialties | 10100 | Visual Display Boards
Division 10 | Specialties | 10150 | Compartments and Cubicles
Division 10 | Specialties | 10200 | Louvers and Vents
Division 10 | Specialties | 10240 | Grilles and Screens
Division 10 | Specialties | 10250 | Service Walls
Division 10 | Specialties | 10260 | Wall and Corner Guards
Division 10 | Specialties | 10270 | Access Flooring
Division 10 | Specialties | 10290 | Pest Control
Division 10 | Specialties | 10300 | Fireplaces and Stoves
Division 10 | Specialties | 10340 | Manufactured Exterior Specialties
Division 10 | Specialties | 10350 | Flagpoles
Division 10 | Specialties | 10400 | Identification Devices
Division 10 | Specialties | 10450 | Pedestrian Control Devices
Division 10 | Specialties | 10500 | Lockers
Division 10 | Specialties | 10520 | Fire Protection Specialties
Division 10 | Specialties | 10530 | Protective Covers
Division 10 | Specialties | 10550 | Postal Specialties
Division 10 | Specialties | 10600 | Partitions
Division 10 | Specialties | 10670 | Storage Shelving
Division 10 | Specialties | 10700 | Exterior Protection
Division 10 | Specialties | 10750 | Telephone Specialties
Division 10 | Specialties | 10800 | Toilet, Bath, and Laundry Accessories
Division 10 | Specialties | 10880 | Scales
Division 10 | Specialties | 10900 | Wardrobe and Closet Specialties
Division 11 | Equipment | 11000 | Equipment
Division 11 | Equipment | 11010 | Maintenance Equipment
Division 11 | Equipment | 11020 | Security and Vault Equipment
Division 11 | Equipment | 11030 | Teller and Service Equipment
Division 11 | Equipment | 11040 | Ecclesiastical Equipment
Division 11 | Equipment | 11050 | Library Equipment
Division 11 | Equipment | 11060 | Theater and Stage Equipment
Division 11 | Equipment | 11070 | Instrumental Equipment
Division 11 | Equipment | 11080 | Registration Equipment
Division 11 | Equipment | 11090 | Checkroom Equipment
Division 11 | Equipment | 11100 | Mercantile Equipment
Division 11 | Equipment | 11110 | Commercial Laundry and Dry Cleaning Equipment
Division 11 | Equipment | 11120 | Vending Equipment
Division 11 | Equipment | 11130 | Audio-Visual Equipment
Division 11 | Equipment | 11140 | Vehicle Service Equipment
Division 11 | Equipment | 11150 | Parking Control Equipment
Division 11 | Equipment | 11160 | Loading Dock Equipment
Division 11 | Equipment | 11170 | Solid Waste Handling Equipment
Division 11 | Equipment | 11190 | Detention Equipment
Division 11 | Equipment | 11200 | Water Supply and Treatment Equipment
Division 11 | Equipment | 11280 | Hydraulic Gates and Valves
Division 11 | Equipment | 11300 | Fluid Waste Treatment Equipment
Division 11 | Equipment | 11400 | Food Service Equipment
Division 11 | Equipment | 11450 | Residential Equipment
Division 11 | Equipment | 11460 | Unit Kitchens
Division 11 | Equipment | 11470 | Darkroom Equipment
Division 11 | Equipment | 11480 | Athletic, Recreational, and Therapeutic Equipment
Division 11 | Equipment | 11500 | Industrial and Process Equipment
Division 11 | Equipment | 11600 | Laboratory Equipment
Division 11 | Equipment | 11650 | Planetarium Equipment
Division 11 | Equipment | 11660 | Observatory Equipment
Division 11 | Equipment | 11680 | Office Equipment
Division 11 | Equipment | 11700 | Medical Equipment
Division 11 | Equipment | 11780 | Mortuary Equipment
Division 11 | Equipment | 11850 | Navigation Equipment
Division 11 | Equipment | 11870 | Agricultural Equipment
Division 11 | Equipment | 11900 | Exhibit Equipment
Division 12 | Furnishings | 12000 | Furnishings
Division 12 | Furnishings | 12050 | Fabrics
Division 12 | Furnishings | 12100 | Art
Division 12 | Furnishings | 12300 | Manufactured Casework
Division 12 | Furnishings | 12400 | Furnishings and Accessories
Division 12 | Furnishings | 12500 | Furniture
Division 12 | Furnishings | 12600 | Multiple Seating
Division 12 | Furnishings | 12700 | Systems Furniture
Division 12 | Furnishings | 12800 | Interior Plants and Planters
Division 12 | Furnishings | 12900 | Furnishings Repair and Restoration
Division 13 | Special Construction | 13000 | Special Construction
Division 13 | Special Construction | 13010 | Air-Supported Structures
Division 13 | Special Construction | 13020 | Building Modules
Division 13 | Special Construction | 13030 | Special Purpose Rooms
Division 13 | Special Construction | 13080 | Sound, Vibration, and Seismic Control
Division 13 | Special Construction | 13090 | Radiation Protection
Division 13 | Special Construction | 13100 | Lightning Protection
Division 13 | Special Construction | 13110 | Cathodic Protection
Division 13 | Special Construction | 13120 | Pre-Engineered Structures
Division 13 | Special Construction | 13450 | Swimming Pools
Division 13 | Special Construction | 13160 | Aquariums
Division 13 | Special Construction | 13165 | Aquatic Park Facilities
Division 13 | Special Construction | 13170 | Tubs and Pools
Division 13 | Special Construction | 13175 | Ice Rinks
Division 13 | Special Construction | 13185 | Kennels and Animal Shelters
Division 13 | Special Construction | 13190 | Site-Constructed Incinerators
Division 13 | Special Construction | 13200 | Storage Tanks
Division 13 | Special Construction | 13220 | Filter Underdrains and Media
Division 13 | Special Construction | 13230 | Digester Covers and Appurtenances
Division 13 | Special Construction | 13240 | Oxygenation Systems
Division 13 | Special Construction | 13260 | Sludge Conditioning Systems
Division 13 | Special Construction | 13280 | Hazardous Material Remediation
Division 13 | Special Construction | 13400 | Measurement and Control Instrumentation
Division 13 | Special Construction | 13500 | Recording Instrumentation
Division 13 | Special Construction | 13550 | Transportation Control Instrumentation
Division 13 | Special Construction | 13600 | Solar and Wind Energy Equipment
Division 13 | Special Construction | 13700 | Security Access and Surveillance
Division 13 | Special Construction | 13800 | Building Automation and Control
Division 13 | Special Construction | 13850 | Detection and Alarm
Division 13 | Special Construction | 13900 | Fire Suppression
Division 14 | Conveying Systems | 14000 | Conveying Systems
Division 14 | Conveying Systems | 14100 | Dumbwaiters
Division 14 | Conveying Systems | 14200 | Elevators
Division 14 | Conveying Systems | 14300 | Escalators and Moving Walks
Division 14 | Conveying Systems | 14400 | Lifts
Division 14 | Conveying Systems | 14500 | Material Handling
Division 14 | Conveying Systems | 14600 | Hoists and Cranes
Division 14 | Conveying Systems | 14700 | Turntables
Division 14 | Conveying Systems | 14800 | Scaffolding
Division 14 | Conveying Systems | 14900 | Transportation
Division 15 | Mechanical | 15000 | Mechanical
Division 15 | Mechanical | 15050 | Basic Mechanical Materials and Methods
Division 15 | Mechanical | 15100 | Building Services Piping
Division 15 | Mechanical | 15200 | Process Piping
Division 15 | Mechanical | 15300 | Fire Protection Piping
Division 15 | Mechanical | 15400 | Plumbing Fixtures and Equipment
Division 15 | Mechanical | 15500 | Heat-Generation Equipment
Division 15 | Mechanical | 15600 | Refrigeration Equipment
Division 15 | Mechanical | 15700 | Heating, Ventilating, and Air Conditioning Equipment
Division 15 | Mechanical | 15800 | Air Distribution
Division 15 | Mechanical | 15900 | HVAC Instrumentation and Controls
Division 15 | Mechanical | 15950 | Testing, Adjusting, and Balancing
Division 16 | Electrical | 16000 | Electrical
Division 16 | Electrical | 16050 | Basic Electrical Materials and Methods
Division 16 | Electrical | 16100 | Wiring Methods
Division 16 | Electrical | 16200 | Electrical Power
Division 16 | Electrical | 16300 | Transmission and Distribution
Division 16 | Electrical | 16400 | Low-Voltage Distribution
Division 16 | Electrical | 16500 | Lighting
Division 16 | Electrical | 16700 | Communications
Division 16 | Electrical | 16800 | Sound and Video

## Sample Master Index
Division | Division Description | CSI Code | CSI Code Description
Division 00 | Special Sections | 00 00 00 | Procurement and Contracting Requirements
Division 00 | Special Sections | 00 10 00 | Solicitation
Division 00 | Special Sections | 00 11 00 | Advertisements and Invitations
Division 00 | Special Sections | 00 20 00 | Instructions for Procurement
Division 00 | Special Sections | 00 21 00 | Instructions
Division 00 | Special Sections | 00 22 00 | Supplementary Instructions
Division 00 | Special Sections | 00 23 00 | Procurement Definitions
Division 00 | Special Sections | 00 24 00 | Procurement Scopes
Division 00 | Special Sections | 00 25 00 | Procurement Meetings
Division 00 | Special Sections | 00 26 00 | Procurement Substitution Procedures
Division 00 | Special Sections | 00 30 00 | Available Information
Division 00 | Special Sections | 00 31 00 | Available Project Information
Division 00 | Special Sections | 00 40 00 | Procurement Forms and Supplements
Division 00 | Special Sections | 00 41 00 | Bid Forms
Division 00 | Special Sections | 00 42 00 | Proposal Forms
Division 00 | Special Sections | 00 43 00 | Procurement Form Supplements
Division 00 | Special Sections | 00 45 00 | Representations and Certifications
Division 00 | Special Sections | 00 50 00 | Contracting Forms and Supplements
Division 00 | Special Sections | 00 60 00 | Project Forms
Division 00 | Special Sections | 00 61 00 | Bond Forms
Division 00 | Special Sections | 00 62 00 | Certificates and Other Forms
Division 00 | Special Sections | 00 63 00 | Clarification and Modifications Forms
Division 00 | Special Sections | 00 65 00 | Closeout Forms
Division 00 | Special Sections | 00 70 00 | Conditions of the Contract
Division 00 | Special Sections | 00 71 00 | Contracting Definitions
Division 00 | Special Sections | 00 72 00 | General Conditions
Division 00 | Special Sections | 00 73 00 | Supplementary Conditions
Division 00 | Special Sections | 00 90 00 | Revisions, Clarifications, and Modifications
Division 00 | Special Sections | 00 91 00 | Precontract Revisions
Division 00 | Special Sections | 00 93 00 | Record Clarifications and Proposals
Division 00 | Special Sections | 00 94 00 | Record Modifications
Division 01 | General Requirements | 01 00 00 | General Requirements
Division 01 | General Requirements | 01 11 00 | Summary of Work
Division 01 | General Requirements | 01 14 00 | Work Restrictions
Division 01 | General Requirements | 01 20 00 | Price and Payment Procedures
Division 01 | General Requirements | 01 24 00 | Value Analysis
Division 01 | General Requirements | 01 30 00 | Administrative Requirements
Division 01 | General Requirements | 01 31 00 | Project Management and Coordination
Division 01 | General Requirements | 01 32 00 | Construction Progress Documentation
Division 01 | General Requirements | 01 33 00 | Submittal Procedures
Division 01 | General Requirements | 01 35 00 | Special Procedures
Division 01 | General Requirements | 01 40 00 | Quality Requirements
Division 01 | General Requirements | 01 41 00 | Regulatory Requirements
Division 01 | General Requirements | 01 42 00 | References
Division 01 | General Requirements | 01 43 00 | Quality Assurance
Division 01 | General Requirements | 01 45 00 | Quality Control
Division 01 | General Requirements | 01 50 00 | Temporary Facilities and Controls
Division 01 | General Requirements | 01 51 00 | Temporary Utilities
Division 01 | General Requirements | 01 52 00 | Construction Facilities
Division 01 | General Requirements | 01 53 00 | Temporary Construction
Division 01 | General Requirements | 01 54 00 | Construction Aids
Division 01 | General Requirements | 01 55 00 | Vehicular Access and Parking
Division 01 | General Requirements | 01 56 00 | Temporary Barriers and Enclosures
Division 01 | General Requirements | 01 57 00 | Temporary Controls
Division 01 | General Requirements | 01 58 00 | Project Identification
Division 01 | General Requirements | 01 70 00 | Execution and Closeout Requirements
Division 01 | General Requirements | 01 71 00 | Examination and Preparation
Division 01 | General Requirements | 01 74 00 | Cleaning and Waste Management
Division 01 | General Requirements | 01 77 00 | Closeout Procedures
Division 01 | General Requirements | 01 80 00 | Performance Requirements
Division 01 | General Requirements | 01 81 00 | Facility Performance Requirements
Division 01 | General Requirements | 01 90 00 | Lifecycle Activities
Division 01 | General Requirements | 01 92 00 | Facility Operation
Division 01 | General Requirements | 01 93 00 | Facility Maintenance
Division 02 | Existing Conditions | 02 00 00 | Existing Conditions
Division 02 | Existing Conditions | 02 21 00 | Surveys
Division 02 | Existing Conditions | 02 22 00 | Existing Conditions Assessment
Division 02 | Existing Conditions | 02 24 00 | Environmental Assessment
Division 02 | Existing Conditions | 02 25 00 | Existing Material Assessment
Division 02 | Existing Conditions | 02 26 00 | Hazardous Material Assessment
Division 02 | Existing Conditions | 02 30 00 | Subsurface Investigation
Division 02 | Existing Conditions | 02 31 00 | Geophysical Investigations
Division 02 | Existing Conditions | 02 32 00 | Geotechnical Investigations
Division 02 | Existing Conditions | 02 40 00 | Demolition and Structure Moving
Division 02 | Existing Conditions | 02 41 00 | Demolition
Division 02 | Existing Conditions | 02 42 00 | Removal of Salvage and Construction Materials
Division 02 | Existing Conditions | 02 43 00 | Structure Relocation
Division 02 | Existing Conditions | 02 50 00 | Site Remediation
Division 02 | Existing Conditions | 02 51 00 | Physical Decontamination
Division 02 | Existing Conditions | 02 52 00 | Chemical Decontamination
Division 02 | Existing Conditions | 02 53 00 | Thermal Decontamination
Division 02 | Existing Conditions | 02 54 00 | Biological Decontamination
Division 02 | Existing Conditions | 02 55 00 | Remediation Soil Stabilization
Division 02 | Existing Conditions | 02 56 00 | Site Containment
Division 02 | Existing Conditions | 02 57 00 | Sink Hole Remediation
Division 02 | Existing Conditions | 02 58 00 | Snow Control
Division 02 | Existing Conditions | 02 60 00 | Contaminated Site Material Removal
Division 02 | Existing Conditions | 02 61 00 | Removal and Disposal of Contaminated Soils
Division 02 | Existing Conditions | 02 62 00 | Hazardous Waste Recovery Processes
Division 02 | Existing Conditions | 02 70 00 | Water Remediation
Division 02 | Existing Conditions | 02 71 00 | Groundwater Treatment
Division 02 | Existing Conditions | 02 72 00 | Water Decontamination
Division 02 | Existing Conditions | 02 80 00 | Facility Remediation
Division 02 | Existing Conditions | 02 81 00 | Transportation and Disposal of Hazardous Materials
Division 02 | Existing Conditions | 02 82 00 | Asbestos Remediation
Division 02 | Existing Conditions | 02 83 00 | Lead Remediation
Division 02 | Existing Conditions | 02 85 00 | Mold Remediation
Division 03 | Concrete | 03 00 00 | Concrete
Division 03 | Concrete | 03 10 00 | Concrete Forming and Accessories
Division 03 | Concrete | 03 20 00 | Concrete Reinforcement
Division 03 | Concrete | 03 30 00 | Cast-In-Place Concrete
Division 03 | Concrete | 03 40 00 | Precast Concrete
Division 03 | Concrete | 03 50 00 | Cast Decks and Underlayment
Division 03 | Concrete | 03 60 00 | Grouting
Division 03 | Concrete | 03 70 00 | Mass Concrete
Division 03 | Concrete | 03 80 00 | Concrete Cutting and Boring
Division 04 | Masonry | 04 00 00 | Masonry
Division 04 | Masonry | 04 20 00 | Unit Masonry
Division 04 | Masonry | 04 40 00 | Stone Assemblies
Division 04 | Masonry | 04 50 00 | Refractory Masonry
Division 04 | Masonry | 04 60 00 | Corrosion-Resistant Masonry
Division 04 | Masonry | 04 70 00 | Manufactured Masonry
Division 05 | Metals | 05 00 00 | Metals
Division 05 | Metals | 05 10 00 | Structural Metal Framing
Division 05 | Metals | 05 20 00 | Metal Joists
Division 05 | Metals | 05 30 00 | Metal Decking
Division 05 | Metals | 05 40 00 | Cold-Formed Metal Framing
Division 05 | Metals | 05 50 00 | Metal Fabrications
Division 05 | Metals | 05 70 00 | Decorative Metals
Division 06 | Woods, Plastics, Composites | 06 00 00 | Woods, Plastics, and Composites
Division 06 | Woods, Plastics, Composites | 06 10 00 | Rough Carpentry
Division 06 | Woods, Plastics, Composites | 06 20 00 | Finish Carpentry
Division 06 | Woods, Plastics, Composites | 06 40 00 | Architectural Woodwork
Division 06 | Woods, Plastics, Composites | 06 50 00 | Structural Plastics
Division 06 | Woods, Plastics, Composites | 06 60 00 | Plastic Fabrications
Division 06 | Woods, Plastics, Composites | 06 70 00 | Structural Composites
Division 06 | Woods, Plastics, Composites | 06 80 00 | Composite Fabrications
Division 07 | Thermal and Moisture Protection | 07 00 00 | Thermal and Moisture Protection
Division 07 | Thermal and Moisture Protection | 07 10 00 | Damp proofing and Waterproofing
Division 07 | Thermal and Moisture Protection | 07 20 00 | Thermal Protection
Division 07 | Thermal and Moisture Protection | 07 30 00 | Steep Slope Roofing
Division 07 | Thermal and Moisture Protection | 07 40 00 | Roofing and Siding Panels
Division 07 | Thermal and Moisture Protection | 07 50 00 | Membrane Roofing
Division 07 | Thermal and Moisture Protection | 07 60 00 | Flashing & Sheet Metal
Division 07 | Thermal and Moisture Protection | 07 70 00 | Roof and Wall Specialties and Accessories
Division 07 | Thermal and Moisture Protection | 07 80 00 | Fire and Smoke Protection
Division 07 | Thermal and Moisture Protection | 07 90 00 | Joint Protection
Division 08 | Openings | 08 00 00 | Openings
Division 08 | Openings | 08 10 00 | Doors and Frames
Division 08 | Openings | 08 30 00 | Specialty Doors and Frames
Division 08 | Openings | 08 40 00 | Entrances, Storefronts, and Curtain Walls
Division 08 | Openings | 08 50 00 | Windows
Division 08 | Openings | 08 60 00 | Roof Windows and Skylights
Division 08 | Openings | 08 70 00 | Hardware
Division 08 | Openings | 08 80 00 | Glazing
Division 09 | Finishes | 09 00 00 | Finishes
Division 09 | Finishes | 09 20 00 | Plaster and Gypsum Board
Division 09 | Finishes | 09 30 00 | Tiling
Division 09 | Finishes | 09 50 00 | Ceilings
Division 09 | Finishes | 09 60 00 | Flooring
Division 09 | Finishes | 09 70 00 | Wall Finishes
Division 09 | Finishes | 09 80 00 | Acoustic Treatment
Division 09 | Finishes | 09 90 00 | Painting and Coating
Division 10 | Specialties | 10 00 00 | Specialties
Division 10 | Specialties | 10 14 00 | Signage
Division 10 | Specialties | 10 31 00 | Manufactured Fireplaces
Division 10 | Specialties | 10 32 00 | Fireplace Specialties
Division 11 | Equipment | 11 00 00 | Equipment
Division 11 | Equipment | 11 30 00 | Residential Equipment
Division 11 | Equipment | 11 40 00 | Foodservices Equipment
Division 11 | Equipment | 11 60 00 | Entertainment Equipment
Division 12 | Furnishings | 12 00 00 | Furnishings
Division 12 | Furnishings | 12 20 00 | Window Treatments
Division 12 | Furnishings | 12 30 00 | Casework
Division 12 | Furnishings | 12 36 00 | Countertops
Division 12 | Furnishings | 12 40 00 | Furnishings and Accessories
Division 13 | Special Construction | 13 00 00 | Special Construction
Division 13 | Special Construction | 13 11 00 | Swimming Pools
Division 13 | Special Construction | 13 20 00 | Special Purpose Rooms
Division 14 | Conveying Equipment | 14 00 00 | Conveying Equipment
Division 14 | Conveying Equipment | 14 10 00 | Dumbwaiters
Division 14 | Conveying Equipment | 14 20 00 | Elevators
Division 14 | Conveying Equipment | 14 30 00 | Escalators and Moving Walks
Division 14 | Conveying Equipment | 14 40 00 | Lifts
Division 21 | Fire Suppression | 21 00 00 | Fire Suppression
Division 21 | Fire Suppression | 21 10 00 | Water-Based Fire Suppression Systems
Division 21 | Fire Suppression | 21 20 00 | Fire Extinguishing Systems
Division 21 | Fire Suppression | 21 30 00 | Fire Pumps
Division 21 | Fire Suppression | 21 40 00 | Fire Suppression Water Storage
Division 22 | Plumbing | 22 00 00 | Plumbing
Division 22 | Plumbing | 22 10 00 | Plumbing Piping and Pumps
Division 22 | Plumbing | 22 11 00 | Facility Water Distribution
Division 22 | Plumbing | 22 30 00 | Plumbing Equipment
Division 22 | Plumbing | 22 40 00 | Plumbing Fixtures
Division 22 | Plumbing | 22 50 00 | Pool and Fountain Plumbing Systems
Division 22 | Plumbing | 22 66 00 | Chemical Waste Systems for Laboratory and Healthcare
Division 23 | Heating, Ventilating, and Air Conditioning | 23 00 00 | HVAC
Division 23 | Heating, Ventilating, and Air Conditioning | 23 10 00 | Facility Fuel Systems
Division 23 | Heating, Ventilating, and Air Conditioning | 23 20 00 | HVAC Piping and Pumps
Division 23 | Heating, Ventilating, and Air Conditioning | 23 30 00 | HVAC Air Distribution
Division 23 | Heating, Ventilating, and Air Conditioning | 23 40 00 | HVAC Air Cleaning Devices
Division 23 | Heating, Ventilating, and Air Conditioning | 23 50 00 | Central Heating Equipment
Division 25 | Integrated Automation | 25 00 00 | Integrated Automation
Division 25 | Integrated Automation | 25 10 00 | Integrated Automation Network Equipment
Division 25 | Integrated Automation | 25 50 00 | Integrated Automation Facility Controls
Division 26 | Electrical | 26 00 00 | Electrical
Division 26 | Electrical | 26 10 00 | Operation and Maintenance of Electrical Systems
Division 26 | Electrical | 26 50 00 | Lighting
Division 26 | Electrical | 26 52 00 | Emergency Lighting
Division 27 | Communications | 27 00 00 | Communications
Division 27 | Communications | 27 10 00 | Structured Cabling
Division 27 | Communications | 27 40 00 | Audio-Video Communications
Division 28 | Electronic Safety & Security | 28 00 00 | Electronic Safety and Security
Division 28 | Electronic Safety & Security | 28 10 00 | Electronic Access Control and Intrusion Detection
Division 28 | Electronic Safety & Security | 28 20 00 | Electronic Surveillance
Division 28 | Electronic Safety & Security | 28 30 00 | Electronic Detection and Alarm
Division 28 | Electronic Safety & Security | 28 40 00 | Electronic Monitoring and Control
Division 31 | Earthwork | 31 00 00 | Landscaping
Division 31 | Earthwork | 31 10 00 | Site Clearing
Division 31 | Earthwork | 31 20 00 | Earth Moving
Division 31 | Earthwork | 31 30 00 | Earth Methods
Division 31 | Earthwork | 31 40 00 | Shoring and Underpinning
Division 31 | Earthwork | 31 60 00 | Special Foundations and Load-Bearing Elements
Division 32 | Exterior Improvements | 32 00 00 | Exterior Improvements
Division 32 | Exterior Improvements | 32 10 00 | Bases, Ballasts, and Paving
Division 32 | Exterior Improvements | 32 14 00 | Unit Paving
Division 32 | Exterior Improvements | 32 16 00 | Curbs and Gutters
Division 32 | Exterior Improvements | 32 17 23 | Pavement Markings
Division 32 | Exterior Improvements | 32 31 00 | Fences and Gates
Division 32 | Exterior Improvements | 32 32 00 | Retaining Walls
Division 32 | Exterior Improvements | 32 80 00 | Irrigation
Division 32 | Exterior Improvements | 32 90 00 | Planting
Division 33 | Utilities | 33 00 00 | Utilities
Division 33 | Utilities | 33 10 00 | Water Utilities
Division 33 | Utilities | 33 30 00 | Sanitary Sewer Utilities
Division 33 | Utilities | 33 36 00 | Utility Septic Tanks
Division 33 | Utilities | 33 40 00 | Storm Drainage Utilities
Division 34 | Transportation | 34 00 00 | Transportation
Division 35 | Waterway and Marine Construction | 35 00 00 | Waterway and Marine Construction
Division 35 | Waterway and Marine Construction | 35 50 00 | Marine Construction and Equipment
Division 40 | Process Integration | 40 00 00 | Process Integration
Division 41 | Material Processing and Handling Equipment | 41 00 00 | Material Processing and Handling Equipment
Division 41 | Material Processing and Handling Equipment | 41 10 00 | Bulk Material Processing Equipment
Division 41 | Material Processing and Handling Equipment | 41 20 00 | Piece Material Handling Equipment
Division 41 | Material Processing and Handling Equipment | 41 40 00 | Container Processing and Packing
Division 41 | Material Processing and Handling Equipment | 41 50 00 | Material Storage
Division 41 | Material Processing and Handling Equipment | 41 60 00 | Mobile Plant Equipment
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 00 00 | Process Heating, Cooling, and Drying Equipment
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 11 00 | Process Boilers
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 12 00 | Process Heaters
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 14 00 | Industrial Furnaces
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 15 00 | Industrial Ovens
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 20 00 | Process Cooling Equipment
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 21 00 | Process Cooling Towers
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 22 00 | Process Chillers and Coolers
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 23 00 | Process Condensers and Evaporators
Division 42 | Process Heating, Cooling, and Drying Equipment | 42 31 00 | Gas Dryers and Humidifiers
Division 43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | 43 00 00 | Process Gas and Liquid Handling, Purification, and Storage Equipment
Division 43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | 43 12 00 | Gas Compressors
Division 43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | 43 13 00 | Gas Process Equipment
Division 43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | 43 15 00 | Process Air and Gas Filters
Division 43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | 43 42 00 | Pressurized Tanks and Vessels
Division 44 | Pollution and Waste Control Equipment | 44 00 00 | Pollution and Waste Control Equipment
Division 44 | Pollution and Waste Control Equipment | 44 10 00 | Air Pollution Control
Division 44 | Pollution and Waste Control Equipment | 44 30 00 | Odor Control
Division 44 | Pollution and Waste Control Equipment | 44 40 00 | Water Pollution Control Equipment
Division 44 | Pollution and Waste Control Equipment | 44 50 00 | Solid Waste Control and Reuse
Division 44 | Pollution and Waste Control Equipment | 44 60 00 | Water Thermal Processing Equipment
Division 45 | Industry Specific Manufacturing | 45 00 00 | Industry Specific Manufacturing
Division 46 | Water and Wastewater Equipment | 46 00 00 | Water and Wastewater Equipment
Division 46 | Water and Wastewater Equipment | 46 20 00 | Water and Wastewater Preliminary Treatment Equipment
Division 46 | Water and Wastewater Equipment | 46 30 00 | Water and Wastewater Chemical Feed Equipment
Division 46 | Water and Wastewater Equipment | 46 40 00 | Water and Wastewater Clarification and Mixing Equipment
Division 46 | Water and Wastewater Equipment | 46 50 00 | Water and Wastewater Secondary Treatment Equipment
Division 46 | Water and Wastewater Equipment | 46 60 00 | Water and Wastewater Advanced Treatment Equipment
Division 48 | Electrical Power Generation | 48 00 00 | Electrical Power Generation
Division 48 | Electrical Power Generation | 48 10 00 | Electrical Power Generation Equipment
Division 48 | Electrical Power Generation | 48 15 00 | Windmills
Division 48 | Electrical Power Generation | 48 70 00 | Electrical Power Generation Testing